## LOEs, IOs, and Objectives
ID | Description | Start Date | End Date | Status | Dependencies
LOE1 | Project visualization tool | 2023-05-10 | 2023-05-20 | At Risk | O1.1,O1.2
LOE2 | Moving in | 2023-05-08 | 2023-06-01 | On Track | O2.1,O2.2
O1.1 | Write input and validation logic | 2023-05-10 | 2023-05-15 | Overdue
O1.2 | Create visual logic | 2023-05-14 | 2023-05-19 | At Risk | O1.2
O2.1 | Clean out room | 2023-05-09 | 2023-05-12 | Complete
O2.2 | Unload boxes | 2023-05-14 | 2023-05-25 | On Track | O2.1